## Architect visit schedule
ARCHITECT VISIT SCHEDULE
Visit No. | Stage | Main checks/ Purpose | Visit Type | Remarks
1 | Pre construction/ Site handover | Existing site conditions, dimensions, levels, structural elements, site constraints, existing MEP points | Mandatory
2 | After foundation layout /start of structural work | Check layout as per drawings, levels, grids, dimensions | Hold point
3 | Column & beam laying | Check column and beam location | Mandatory
4 | Before slab casting | Check shuttering, slab level, shafts, openings,conduits if any, sleeves provision, structure | Hold point
5 | Before/ During walling | Check layout, room dimensions, D & W openings | Mandatory
6 | Before Wall Chasing | Switch/socket locations, heights, TV/data points, plumbing points, AC points, special electrical requirements | Hold point
7 | Plumbing/ electrical first fix check before plaster | Loction & height check, routine check, | Hold point
8 | After MEP First Fix – Before Plaster | Electrical & plumbing routing, pipe sizes, slopes, sleeves, concealed boxes, AC piping/drain, coordination with furniture/ceiling | Hold point
9 | After Bathroom Waterproofing | Leakage test, water retention, drain slope, wall treatment | Hold point
10 | After floor PCC | Floor levels, slopes, bathroom slope, finished floor levels, thresholds | Mandatory
11 | During flooring/ Tiling | Tile layout, starting point, pattern, joints, border/cut pieces, drain alignment, slope | As required
12 | During/ After false ceiling framework & wiring | Ceiling level, cove details, AC diffusers(if any), curtain pockets, access panels/ trap doors, lights location, fan point, plywork for chandeliers/ AC/ curtains, profile channels | Hold point |  | REMARKS: BEFORE FALSE CEILING: CEILING ELETRICAL CHECK
13 | After false ceiling POP | Ceiling level, corners, cut-outs, cove details, light locations mark | Mandatory
14 | Before Fixed Furniture / Carpentry | Final wall/floor dimensions, electrical & plumbing points, furniture clearances, appliance dimensions, fixing requirements | Hold point
15 | During Fixed Furniture / Wall Panelling | Material, alignment, dimensions, edge details, hardware, electrical integration, junctions | As Required
16 | Before Painting / Final Finishes | Surface preparation, putty, primer, colour/sample approval, repaired surfaces, protection of completed works | Hold Point
17 | During Final Finishes | Paint finish, wallpaper, polish/PU, glass, mirrors, hardware, visible junctions | As Required
18 | After Fixtures and final installation | Sanitary fixtures, switches, lights, fans, AC grilles, hardware, accessories, furniture alignment | Mandatory
19 | Pre handover inspections | Complete snag inspection: finishes, dimensions, functionality, MEP, furniture, doors/windows, cleaning | Mandatory (Critical)
20 | Snag List closure check | Verify all snag points are rectified; check rework quality | Mandatory
21 | Final handoverr | Final finishes, cleanliness, protection removal, drawings/documents, warranties/manuals, handover checklist | Mandatory

## Snag list
SNAG LIST
S. No. | Floor | Room | Category | Observation | Photo | Scope | Status | Remarks

## Quality check list (hidden)
S. no.
1 | Excavation
2 | PCC work
3 | Formwork
4 | Concreting
6 | Brickwork
7 | Waterproofing
8 | Plaster work
9 | Waterproofing
10 | Plumbing
11 | Electrical & Lighting
12 | HVAC
13 | False ceiling
14 | Flooring work
15 | Paint work
12 | Kitchen inspection
13 | Wardrobe inspection
14 | Bathroom inspection
15 | Doors,windows & glazing